TMA Project Number 16-149

Ebuilder Project Number 100092

Hewitt 232/233 Rehab

Meeting Minutes

Week Four, Week Of January 16, 2017

Project Scope

* New Ceiling Grid/Tile
* New 2x2 LED lighting fixtures
* New artwork LED track lighting
* New closet door system
* New Walker Display System
* New carpet, chair rail, cove base
* New Smoke Alarm, tied to panel
* New flat panel display, smart TV

Project Schedule

* Demolition: 12/20/2016 thru 12/28/2016
* Construction 12/29/2016 thru 1/22/2017

Weekly accomplishments during the week of 1/16/2017 and future schedule.

BTC, BTF, EL, PL, CTS

* Track lighting is complete
* Electrical to be complete by 1/22.
* Alarms to be complete by 1/20.
* HVAC is complete.
* Customer has submitted to BTC a closet door system option. An RFQ has been sent to supplier.
* Ceiling is complete.
* Painting is complete.
* Chair rail, Walker Display System and flat panel mount to be complete by 1/20.
* Flooring to be complete by 1/22.